## RICE Matrix
GYMFIX ¦ PHASE 4 — RICE PRIORITISATION
Illustrative planning assumptions only. Reach = affected interactions per 100 hypothetical monthly maintenance interactions.
Feature | Reach / 100 | Impact | Confidence | Effort (person-weeks) | RICE Score | Proposed Scope | Reasoning
Centralised ticket dashboard | 95 | 3 | 60% | 2 |  | Must | Core workflow; dependencies
Repair status tracking | 90 | 2 | 60% | 1.5 |  | Must | Visibility hypothesis
Ticket assignment | 65 | 3 | 60% | 1.5 |  | Must | Accountability
QR-based fault reporting | 80 | 2 | 60% | 1 |  | Must | Reporting entry point
Repair blocker tracking | 55 | 2 | 60% | 1.5 |  | Should | Parts and technician delays
Fault photo upload | 55 | 1 | 40% | 1 |  | Could | Weak direct evidence
Maintenance history | 45 | 1 | 60% | 2 |  | Should | Useful over time
Member notifications | 60 | 1 | 40% | 2 |  | Could | Privacy and delivery complexity
Multi-branch dashboard | 25 | 1 | 40% | 3 |  | Later | Not needed for single-site pilot
Predictive maintenance | 10 | 2 | 40% | 8 |  | Later | Requires historical data

## Decision Log
Feature | Decision | Reason / Trade-off | Validation needed
Ticket creation + dashboard | MVP | Minimum complete reporting-to-resolution workflow | Can staff locate and manage incoming tickets?
Ticket assignment | MVP | Establish clear owner; core operational value | Can staff assign tickets without guidance?
Repair status | MVP | Visibility for members and staff | Can users find accurate status?
QR reporting | MVP | Fast equipment identification; test adoption | Is scanning actually preferred?
Repair blocker tracking | MVP-lite | One optional blocker field; avoid complex inventory workflows | Do operators use this field?
Maintenance history | Later | Requires sufficient historical records | Is it useful to managers?
Photo upload | Later | Storage/moderation and privacy trade-off | Does it improve diagnostic clarity?
Notifications | Later | Consent and delivery complexity | Do members want notifications?
Multi-branch | Later | Single-site pilot first | Is multi-site need real?
Predictive maintenance | Later | No training dataset or validated demand | Are fault histories sufficient?

## Scoring Guide
Measure | Definition / guidance
Reach | Estimated affected interactions per 100 hypothetical monthly maintenance interactions. NOT actual users.
Impact | 3 massive; 2 high; 1 medium; 0.5 low; 0.25 minimal.
Confidence | 0.8 relatively strong evidence; 0.6 partial evidence; 0.4 weak evidence. These are subjective estimates.
Effort | Illustrative person-weeks, not validated engineering estimates.
RICE | Reach x Impact x Confidence / Effort. Scores are only comparable within these assumptions.
MVP override | A feature can be essential to the complete workflow even if RICE is not highest.
Caveat | Do not interpret 100 interactions as 100 independent people or actual demand.